# #OneOxford

The Full Picture | Confidential | For Team Discussion

Thank you for coming together on this. Now that we're meeting, I want to share the full vision — including the branding and narrative that ties everything together.

We also have a genuine challenge: 100+ people are ready to feature. That's exciting — but it's also a technical and design problem. I need your expertise to figure out how we actually make this work at scale.

## The Brand: #OneOxford

The campaign name is #OneOxford. The word "One" works on multiple levels — and that flexibility is the point.

One Thing — "What's your one thing you'd change about Oxford?" (our core question)

One Community — Undergrads and postgrads together, not two separate worlds

One Standard — We're the #1 university, let's act like it

One Voice — Every individual matters

One Vote — Your vote counts (for GOTV messaging)

One Oxbridge — I'm the only candidate with leadership experience at both Cambridge and Oxford

This flexibility means the brand can hold any issue — funding, mental health, careers, college disparities — while staying coherent. Everything ladders up to #OneOxford.

## The Core Mechanic

The insight we're building on: if people feature, they share.

When someone sees their face on a website, their voice in a video, their name as part of a community — they want to tell people about it. Their friends see it. Some of those friends join. The campaign becomes self-amplifying.

The math: 100 people × 200 connections each = 20,000 potential impressions. If even 5% engage, that's 1,000 people. If 10% of those join, we have 100 more. And it compounds.

But this only works if we make featuring easy, looking good easy, and sharing easy. That's the design challenge.

## The Scale Challenge

We currently have 100+ people scheduled to feature. During the active campaign (Feb 3-12), we want that to grow — ideally anyone can add themselves.

This creates real challenges:

Collection: How do we gather photos, quotes, and video clips from 100+ people without it becoming a nightmare? What's the smoothest workflow?

Storage: Where do all these assets live? How do we organise them?

Display: How do we show 100+ faces beautifully? How does filtering work? How do individual profiles look?

Self-submission: During the live campaign, how do new people add themselves? Do we need approval, or can it be automatic? What if we get 20 submissions in one day?

Sharing: How do we make each profile shareable? What about social previews? How do we make sharing feel natural, not forced?

Video: We want a community video with 50+ clips (2-4 seconds each). How do we collect these efficiently? How do we let each person know their timestamp so they can share?

## What the Website Needs to Do

The website serves two purposes: community showcase AND campaign hub. It needs:

Community Showcase (the differentiator)

• Wall of faces — grid/gallery of 100+ photos

• Filter by college — so visitors can find people they know

• Individual profiles — photo, name, college, subject, their "one thing" (text or video)

• Shareable profile links — e.g. oneoxford.uk/people/sarah-balliol

• "Add yourself" form — upload photo, enter details, submit

Campaign Essentials

• My story / About — who I am, why I'm running

• Manifesto / Platform — what I stand for

• Videos — personal story video + community video embedded

• Events / Socials — what's happening, how to get involved

• How to vote — clear info, link when voting opens

• Required disclaimer — per SU rules

## The Videos

Video 1: My Story (1-2 min)

Personal, direct to camera, why I'm running. I'll film this myself — authenticity over production value.

Video 2: Community Video (60-90 sec)

Quick clips of 50+ people, each saying their "one thing" (2-4 seconds each). Energy, music, quick cuts. Ends with a unifying moment — everyone saying "One Oxford" in quick succession.

Challenge: Every person featured needs to know their timestamp so they can share the exact moment they appear. How do we manage this?

## Events & Socials

The campaign should bring people together in real life. I'd rather spend budget on a social or food than on traditional campaign materials. The website should make events visible — being part of #OneOxford means being invited into something real, not just asked to vote.

## Constraints (Reminder)

Budget: £60 maximum — Free solutions essential. I'd prefer to spend on socials, not materials.

Launch: Tuesday 3 February, 9am — Everything ready to go live at 9am sharp.

Voting: 9-12 February — Active campaign runs until 8pm on the 12th.

Disclaimer required — "If you have any concerns about the contents of this page, please contact the Deputy Returning Officer on elections@oxfordsu.ox.ac.uk"

## Timeline

| Period | Focus |
| --- | --- |
| Now – 25 Jan | Planning, architecture decisions, initial asset collection |
| 26 Jan – 2 Feb | Intensive build: collect assets, build website, edit videos, test |
| 2 Feb evening | Final checks — everything ready to deploy |
| 3 Feb, 9am | LAUNCH |
| 3 – 12 Feb | Active campaign: onboard new supporters, events, GOTV |

My final assessment is on the 26th. After that, I'm going 120% on this through to the end of voting.

## Questions for Discussion

These are the things I need your expertise on:

Collection workflow:

• What's the best way to collect photos, quotes, and video clips from 100+ people?

• Do we use a form? Google Drive? Something else?

• How do we maintain quality control without creating bottlenecks?

Technical architecture:

• What's the simplest stack that handles 100+ profiles with filtering and self-submission?

• Free hosting options?

• How do we handle video — YouTube embeds, direct upload, something else?

Design:

• How do we display 100+ photos in a way that looks good and loads fast?

• What should individual profiles look like?

• How do we make the "add yourself" flow genuinely effortless?

Sharing mechanics:

• How do we generate shareable links with good social previews?

• Any way to make sharing even easier (pre-written text, downloadable graphics)?

• For the community video — how do we communicate timestamps to 50+ people?

What am I not thinking about?

## Let's Build This

This is a genuine design and engineering challenge. I don't have all the answers — that's why I need you.

What we build together should be something you can all genuinely reference — portfolios, applications, conversations. Real product, real users, real impact.

I think we can build something special. Let's figure out how.

David